## Sheet1
Bi Monthly Compliance Audit Tool
Smith Constructions
| Site | Manjimup
| Issue Date | 2010-01-21
Distribution:
Superviser/Site Manager
| Contract Administrators |  | Overall Audit Score | 85.85%
Systems Manager
Construction Manager
Commercial Director
Construction Director
Bi-Monthly Compliance Audit Tool
This bi-monthly assessment will assess each site against its Safety Management Plan and statutory requirements
Prepared By: |  |  | Ronel Spence
| Definitions | SSMP - Site Safety Management Plan
OSH Act - Occupational safety & Health Act, 1984
OSH Reg - Occupational Safety & Health Regulations 1996
AS4801 - Australian Standard 4801 for Occupational Health & Safety Management Systems
| Rating Scale: | * | Not Applicable | Use if criteria not applicable to the job or unable to be assessed at time of audit.
|  | 1 | Unacceptable: | Raise NCR, immediate intervention required by Construction Coordinator or Construction Manager)
|  | 2 | Poor: | Issue Safety Observation, Construction Coordinator notified.
|  | 3 | Fair: | Basic compliance not met, some remedial action required within next 24 hours.
|  | 4 | Good: | Not best practice - requires improvement
|  | 5 | Best Practice: | Best practice (continue to strive in order to maintain this level)
Item No. | Item Description | Applicable Legislation / Standard / Procedure | Findings | Loading | Rating | Total Score | Action By | Due Date | Date Complete
Section 1 - Site Safety Management Plan
1 | A copy of the safety management plan is available in the main office | OSH Reg 3.142 & AS4801 Clause 4.3.4 |  | 1 | 5 | 5
2 | The safety management plan and company policies are discussed at the site induction. | AS4801 Clause 4.2 & 4.4.3.2 |  | 1 | 5 | 5
3 | Company Safety Policy is displayed in prominent locations | AS4801 Clause 4.2 & 4.4.3.2 |  | 1 | 5 | 5
4 | Company Rehabilitation Policy is displayed in prominent locations | Workers Comp & Injury Mngt Act s155B & 155C |  | 1 | 5 | 5
5 | Company Environmental Policy is displayed in prominent locations |  |  | 1 | 5 | 5
6 | Company Quality Policy is displayed in prominent locations |  |  | 1 | 5 | 5
7 | Company Non Smoking Policy is displayed in prominent locations | OSH reg 3.44B & 3.44G |  | 1 | 5 | 5
|  |  | Total Possible Score | 35
|  |  | Actual Applicable Score | 35 |  | 35 | 100%
Section 2 - Legislation, Australian Standards, Codes of Practice and Guidelines
8 | A copy of the Act and Regulations are available | OSH Reg 3.2, |  | 1 | 5 | 5
9 | Australian Standards are available | OSH Reg 3.2, |  | 1 | 5 | 5
10 | Relevant Codes of Practice are available. | OSH Reg 3.2, |  | 1 | 5 | 5
11 | A copy of the client specification manual is on site and available |  |  | 1 | 5 | 5
|  |  | Total Possible Score | 20
|  |  | Actual Applicable Score | 20 |  | 20 | 100%
Section 3 – Communication and Consultation
12 | A notice board is available on site | AS4801 clause4.4.3.2 |  | 1 | 5 | 5
13 | Appropriate signage is displayed around site – including restricted access, no entry etc. (exclude fire extinguishers - this covered under #72) | OSH Reg 3.11 |  | 1 | 5 | 5
14 | Organization chart is displayed in a prominent location | AS4801 clause4.4.3.2 |  | 1 | 5 | 5
15 | Section 19 and 20 of the OSH Act is posted on the notice board. | OSH Act s 19 & 20, AS4801 clause 4.4.3.2 |  | 1 | 5 | 5
16 | The site has a nominated safety representative | OSH Act s 29 | Procedure exists to elect one if requested. Site safety managed by Smith's. | 1 | 5 | 5
17 | Formal site meetings are held, which includes client representatives, Smith Constructions and Architect. | AS4801 clause 4.4.3.2 |  | 1 | 5 | 5
18 | A record of the meetings are available for reference. | AS4801 clause 4.4.3.2 |  | 1 | 5 | 5
19 | Accident/Incident Report forms are being completed for every incident on site. | OSH reg 3.5/3.142(2c), AS4801 clause 4.5.2 |  | 1 | 5 | 5
20 | Incident Forms are being forwarded to the Safety and Training Co-ordinator on a timely basis (within 24 hours) | OSH reg 3.5/3.142(2c), AS4801 clause 4.5.2 |  | 1 | 5 | 5
21 | Incidents are being entered on to the site Incident Register | OSH reg 3.5/3.142(2c), AS4801 clause 4.5.2 |  | 1 | 5 | 5
22 | The hazard register has been completed for the site. | OSH Reg 3.141 |  | 1 | 5 | 5
23 | The hazard register has been reviewed within the last 6 months. | OSH Reg 3.141 |  | 1 | 5 | 5
24 | Hazard Treatment reports have been completed for all hazards that are required to be actioned. | OSH Reg 3.141 |  | 1 | 5 | 5
25 | Toolbox meetings are being held and there are minutes available of the meeting. | AS4801 clause 4.4.3.2 |  | 2 | 5 | 10
26 | There is a copy of the most recent toolbox minutes on the site notice board. | AS4801 clause 4.4.3.2 |  | 1 | 5 | 5
27 | Competed JSA’s are kept on a central file and recorded on the JSA register | OSH reg 3.143, AS4801 clause 4.4.6 |  | 1 | 5 | 5
28 | A site audit schedule has been created and is being used | OSH reg 3.141, AS4801 clause 4.5.4 |  | 1 | 5 | 5
29 | A copy of completed audits (internal and external) are available | OSH reg 3.141 |  | 1 | 5 | 5
30 | Information on notice board is current and includes such items as Policy, Emergency Contacts and First Aid Contacts | OSH reg 3.8/3.10/3.12 |  | 1 | 5 | 5
|  |  | Total Possible Score | 100
|  |  | Actual Applicable Score | 100 |  | 100 | 100%
Section 4 – Responsibilities and Accountabilities
31 | Job descriptions for each job on the organization chart is available | OSH reg 3.142(2a) |  | 1 | 5 | 5
32 | A copy of preferred contractors and contact details is available on site |  |  | 1 | 5 | 5
33 | Sub-Contractors on site have current pre-qualifications. | OSH Act s19, AS4801 clause 4.4.6.2 |  | 1 | 5 | 5
34 | Sub-Contractors on site have been reviewed | OSH Act s19, AS4801 clause 4.4.6.2 |  | 1 | 5 | 5
35 | Site Supervisor has reviewed and approved all JSA's prior to commencement of the nominated activities. | OSH reg 3.143, AS4801 clause 4.4.6, SSMP s 3.11 & 8.1 |  | 2 | 5 | 10
36 | Non Conformance Reports issued on this site have been actioned and closed out | OSH reg 3.143, AS4801 clause 4.5.4 |  | 1 | 5 | 5
|  |  | Total Possible Score | 35
|  |  | Actual Applicable Score | 35 |  | 35 | 100%
Section 5 – Hazard Identification, Risk Assessment and Control
37 | Plant on to and off site register form has been completed and updated according to plant movement. | OSH reg , AS4801 clause 4.5.31 |  | 1 | 5 | 5
38 | Plant condition report form completed for every piece of plant on the register | OSH regs 4.14/4.20/4.28/4.34, AS4801 clause 4.4.6 |  | 2 | 5 | 10
39 | Pre-start checklists are being used and recorded in central file. | OSH regs 4.14/4.20/4.28/4.34, AS4801 clause 4.4.6 |  | 2 | 5 | 10
40 | A record of operator competency is available on site or such records are accessible. | OSH Act s19, OSH regs 3.136/3.141/6.4, AS4801 clause 4.4.2 |  | 2 | 5 | 10
41 | A completed register of electrical plant and equipment is available on site. | OSH reg 3.63, AS4801 clause 4.4.4 |  | 1 | 5 | 5
42 | An electrical tag colour code sign is in place. | OSH Reg 3.11, SSMP s5.2 & 5.35 |  | 1 | 5 | 5
43 | Weekly safety and housekeeping inspection form is being completed periodically | OSH reg 3.141, AS4801 clause 4.5.4 |  | 3 | 5 | 15
44 | Cranes and lifting equipment on site has appropriate certification | OSH reg 3.51/4.34/4.37 |  | 2 | 5 | 10
45 | PPE supplies are fully stocked and available | OSH regs 3.32/3.33/ 3.34/3.35/ 3.36 |  | 1 | 5 | 5
46 | A hazardous materials register is available and up to date | OSH reg 5.13 |  | 1 | 5 | 5
47 | MSDS Sheets are available for all chemicals on site | OSH reg 5.11 |  | 2 | 5 | 10
48 | Storage of hazardous materials is up to standard | OSH reg 5.11, SSMP s 5.14 |  | 1 | 5 | 5
49 | A list of lifting equipment and harnesses etc is available and up to date. | OSH reg 3.51/4.34/4.37, SSMP s 5.10 |  | 1 | 5 | 5
50 | Danger and Out of Service Tags are available on site and in use | OSH reg 4.37A |  | 2 | 5 | 10
51 | Site security fence in place where required. | OSH reg 3.23 |  | 1 | 5 | 5
52 | Ladders comply with Australian Standards | OSH reg 3.26 |  | 2 | 5 | 10
|  |  | Total Possible Score | 125
|  |  | Actual Applicable Score | 125 |  | 125 | 100%
Section 6 – Training
53 | Each employee (including sub contractors) on site has been inducted and records are kept of these inductions | OSH reg 3.136, AS4801 clause4.4.2 |  | 3 | 5 | 15
54 | Each employee (including sub contractors) on site has a Construction Induction or Safety Awareness Training Card |  |  | 2 | 5 | 10
55 | Attendance/Visitor book is being completed effectively |  |  | 1 | 5 | 5
56 | Employee & Sub-contractor training records are kept on file | OSH Act s19, OSH regs 3.136/3.141/6.4, AS4801 clause 4.4.2 |  | 2 | 5 | 10
|  |  | Total Possible Score | 40
|  |  | Actual Applicable Score | 40 |  | 40 | 100%
Section 7 – Administration
57 | Document control process for documents is being followed (ie most recent copy of documents available) | AS4801 clause 4.4.4 |  | 1 | 5 | 5
|  |  | Total Possible Score | 5
|  |  | Actual Applicable Score | 5 |  | 5 | 100%
Section 8 – Sub – Contractor Management General
58 | Suitable PPE is available for each sub-contractor employees | OSH regs 3.32/3.33/ 3.34/3.35/ 3.36 |  | 1 | 5 | 5
59 | The sub-contractor has completed a Job Safety Analysis for each main task or as required | OSH reg 3.143, AS4801 clause 4.4.6 |  | 2 | 5 | 10
60 | Sub-contractors comply with the companies Incident Reporting Procedure | OSH reg 3.5/3.142(2c), AS4801 clause 4.5.2 |  | 1 | 5 | 5
61 | The sub-contractor scaffolding is up to required standards | OSH reg 3.67 |  | 3 | 5 | 15
62 | All sub-contractors have supplied our company with a copy of their portable electrical equipment | OSH reg 3.63, AS4801 clause 4.4.4 |  | 1 | 5 | 5
63 | The sub-contractor has provided our company with a copy of MSDS Sheet for each chemical they use on site or can produce the MSDS sheet on request. | OSH reg 5.11 |  | 2 | 5 | 10
64 | Sub-contractor plant and machinery is subject to scheduled maintenance, pre-start checks and appropriate certification. | OSH regs 4.14/4.20/4.28/4.34, AS4801 clause 4.4.6 |  | 2 | 5 | 10
|  |  | Total Possible Score | 60
|  |  | Actual Applicable Score | 60 |  | 60 | 100%
Section 9 – Health Management
65 | First aid box is available on site and fully stocked | OSH reg 3.12, AS4801 clause 4.4.7 |  | 2 | 5 | 10
66 | First aid box is checked monthly and a record is kept of that inspection | OSH reg 3.12, AS4801 clause 4.4.7, SSMP s9.2 |  | 2 | 5 | 10
|  |  | Total Possible Score | 20
|  |  | Actual Applicable Score | 20 |  | 20 | 100%
Section 10 – Emergencies
67 | Air horn is available and being used | OSH reg 3.10, AS4801 clause 4.4.7 |  | 1 | 5 | 5
68 | A current site plan is available and displayed | OSH reg 3.10, AS4801 clause 4.4.7, SSMP s 10.1 |  | 1 | 5 | 5
69 | Emergency Evacuation Muster Point Signs available and being used | OSH reg 3.10, AS4801 clause 4.4.7 |  | 1 | 5 | 5
70 | Evacuation Drills are being conducted and a record is kept of those drills | OSH reg 3.10, AS4801 clause 4.4.7 |  | 2 | 5 | 10
71 | Emergency evacuation procedure is in place. | OSH reg 3.10, AS4801 clause 4.4.7 |  | 1 | 5 | 5
72 | Fire extinguishers are available and correctly sign posted. | OSH reg 3.9, AS4801 clause 4.4.7 |  | 2 | 5 | 10
|  |  | Total Possible Score | 40
|  |  | Actual Applicable Score | 40 |  | 40 | 100%
Walk Around Inspection
73 | Electrical equipment is tagged according to the corresponding quarter | OSH reg 3.61/3.62, AS3012 |  | 3 | 5 | 15
74 | No power cord is to exceed 30m in length & is in good condition | OSH reg 3.61/3.62, AS3012 |  | 2 | 5 | 10
75 | Power cables are elevated off the ground and not in water or managed in appropriate manner | OSH reg 3.61/3.62, AS3012 |  | 2 | 5 | 10
76 | Appropriate isolation process is in place and being used | OSH reg 4.37/4.37A |  | 2 | 5 | 10
77 | Only appropriate tools are being used for the job | OSH reg 4.37(d) |  | 2 | 5 | 10
78 | Appropriate guarding is in place on machinery | OSH reg 4.29(i) |  | 2 | 5 | 10
79 | Lunchroom and offices are of a reasonable housekeeping standard | OSH regs 3.17/3.20, SSMP s 5.8/5.33 |  | 1 | 5 | 5
80 | Potable hot and cold water is available. | OSH reg 3.16 |  | 1 | 5 | 5
81 | Holes and excavations surrounded by barricading / bunting, caps on pegs/stakes (adequate protection provided to personnel) | OSH reg 3.109 |  | 2 | 5 | 10
82 | All scaffolds above 4m have a Scafftag attached | OSH reg 3.67 |  | 2 | 5 | 10
83 | All scaffolds below 4m are up to standard | OSH reg 3.67 |  | 2 | 5 | 10
84 | Appropriate PPE being worn for the tasks that are being performed | OSH regs 3.32/3.33/ 3.34/3.35/ 3.36 |  | 2 | 5 | 10
85 | Housekeeping standard is to be high | OSH reg 3.17 |  | 2 | 5 | 10
86 | Fire extinguishers are all fully charged and within service date | OSH reg 3.9, AS4801 clause 4.4.7 |  | 2 | 5 | 10
|  |  | Total Possible Score | 135
|  |  | Actual Applicable Score | 135 |  | 135 | 100%
Sub Contractor Spot Audit |  |  | Place Name of Subcontractor here
87 | All personnel signed onto site - sign in & out is required by all persons, each day. |  |  | 1 | 5 | 5
88 | All personnel have received a Smith Constructions site specific induction. | OSH reg 3.136, AS4801 clause4.4.2 |  | 2 | 5 | 10
89 | Evidence of qualifications provided for all sub-contractor employees. | OSH reg 3.136, AS4801 clause4.4.2 |  | 1 | 5 | 5
90 | Mandatory qualifications in place for persons performing high risk tasks. | OSH reg 6.2(1) |  | 3 | 5 | 15
91 | Provide copy of JSA’s for all applicable tasks | OSH reg 3.143, AS4801 clause 4.4.6, SSMP s 3.11 & 8.1 |  | 3 | 5 | 15
92 | Material Safety Data Sheets (MSDS’s) for all items on list. | OSH reg 5.11, SSMP s 5.14 |  | 1 | 5 | 5
93 | All electrical equipment correctly tagged | OSH reg 3.61/3.62, AS3012, SSMP s 5.2 |  | 1 | 5 | 5
94 | Complete Plant Condition Reports and associated plant inspection checklist (available from the site supervisor) | OSH regs 4.14/4.20/4.28/4.34, AS4801 clause 4.4.6, SSMP s 5.1/8.2 |  | 1 | 5 | 5
95 | Copy of current registration & inspection certificates for Cranes (including concrete booms), EWP’s, Scissor Lifts, and any other plant requiring registration. | OSH reg 3.51/4.34/4.37 |  | 1 | 5 | 5
96 | Appropriate PPE being worn for the tasks that are being performed | OSH regs 3.32/3.33/ 3.34/3.35/ 3.36 |  | 2 | 5 | 10
|  |  | Total Possible Score | 80
|  |  | Actual Applicable Score | 80 |  | 80 | 100%
Tilt Panel Documentation (appendix B docs of COP)
OSH reg 3.88 applies to all sections of tilt up panel work. AS3850
Planning: Sheet 1
97 | Names of persons responsible for actions and dates items were initiated and completed are complete. | OSH reg 3.88A |  | 1 | 5 | 5
Key Evidence required
97.1 | Copy of notification to Worksafe to construct panels | " " |  | 1 | 5 | 5
97.2 | Work method Statements/ JSA’s for site preparation, panel construction, panel erection, & structural steel installation. | " " |  | 1 | 5 | 5
97.3 | Shop drawings approved by Project Design Engineer. | " " |  | 1 | 5 | 5
97.4 | Shop drawings and layout plant approved by engineer. | " " |  | 1 | 5 | 5
Panel Properties: Sheet 3
98 | Design Engineer named. Sheet complete. | OSH reg 3.88B |  | 1 | 5 | 5
Panel Properties: Sheet 4
99 | Names of persons responsible for actions and dates items were initiated and completed are complete. | OSH reg 3.88B |  | 2 | 5 | 10
100 | Quality Control: Sheet 5
100.1 | Design Engineer named. Drawing revision noted. | OSH reg 3.88B |  | 1 | 5 | 5
100.2 | Bondbreaker application dates complete. | " " |  | 1 | 5 | 5
100.3 | Reinforcing, Hardware, & Services installation dates complete. Poured date complete. | " " |  | 1 | 5 | 5
100.4 | Test result & date of test complete. | " " |  | 1 | 5 | 5
100.5 | Signatures in place re: quality supervision & quality inspection (usully site supervisor), Authorised to lift By (licenced rigger). | " " |  | 2 | 5 | 10
100.6 | Manufacturers statement of compliance signature (site supervisor). | " " |  | 2 | 5 | 10
100.7 | Key Evidence required – panel Quality Inspection checklist in accordance with section 6.7 of COP, concrete test reports. | " " |  | 2 | 5 | 10
Erection: Sheet 6
101 | Names of persons responsible for actions and dates items were initiated and completed are complete. | OSH reg 3.88C |  | 1 | 5 | 5
102 | Incorporation into Final Structure: Sheet 7
102.1 | Names of persons responsible for actions and dates items were initiated and completed are complete. | OSH reg 3.88E |  | 1 | 5 | 5
102.2 | Key Evidence required – Structural Steel Erectors - induction records, copies/verification of qualifications (eg/ crane, rigger, dogman, EWP licences), JSA. | " " |  | 2 | 5 | 10
102.3 | Structural Steel drawings issued for construction. | " " |  | 1 | 5 | 5
103 | Bracing & Torque Register: Sheet 8
103.1 | Erection Design Engineer, Project Design Engineer, & Rigging Contractor are named. | OSH reg 3.88D |  | 1 | 5 | 5
103.2 | Document complete for both A & B prop on each panel. | " " |  | 1 | 5 | 5
103.3 | “Insp/Cert” is completed with Project Design Engineer Name and date of prop removal recorded under “release” | " " |  | 1 | 5 | 5
103.4 | Key Evidence required – signed authority from Project Design Engineer stating approval to remove temporary props (document should specify either all or nominated panel numbers). | " " |  | 2 | 5 | 10
|  |  | Total Possible Score | 140
|  |  | Actual Applicable Score | 140 |  | 140 | 100%
| SUMMARY |  |  | Applicable Score |  | Actual Score
| Section 1 - Site Safety Management Plan |  |  | 35 |  | 35 | 100%
| Section 2 - Legislation, Australian Standards, Codes of Practice and Guidelines |  |  | 20 |  | 20 | 100%
| Section 3 – Communication and Consultation |  |  | 100 |  | 100 | 100%
| Section 4 – Responsibilities and Accountabilities |  |  | 35 |  | 35 | 100%
| Section 5 – Hazard Identification, Risk Assessment and Control |  |  | 125 |  | 125 | 100%
| Section 6 – Training |  |  | 40 |  | 40 | 100%
| Section 7 – Administration |  |  | 5 |  | 5 | 100%
| Section 8 – Sub – Contractor Management General |  |  | 60 |  | 60 | 100%
| Section 9 – Health Management |  |  | 20 |  | 20 | 100%
| Section 10 – Emergencies |  |  | 40 |  | 40 | 100%
| Walk Around Inspection |  |  | 135 |  | 135 | 100%
| Sub Contractor Spot Audit |  |  | 80 |  | 80 | 100%
| Tilt Panel Documentation (appendix B docs of COP) |  |  | 140 |  | 140 | 100%
|  |  | Audit Score | 835 |  | 835 | 100%
Conclusion